## Cover Page
Big Data
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2026-02-24
SIC-25-26-Team 462
COVID-19 Pandemic Data Analysis and Trend Prediction using Apache Spark and Machine Learning
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19 | 2021-11-20
1. Project Planning & Setup |  |  | 2026-02-21 | 2026-02-21 | Prince Bhatia | Project charter and role assignment | Done | bar: 2021-11-01 to 2021-11-13
| 1.1 Problem statement and objective finalization |  | 2026-02-21 | 2026-02-21 | Prince Bhatia | Approved project objective | Done | bar: 2021-11-01 to 2021-11-12
| 1.2 Environment setup (Spark/Python/Jupyter) |  | 2026-02-21 | 2026-02-21 | Sourabh Panchal | Working development environment | Done | bar: 2021-11-01 to 2021-11-08
2. Data Acquisition |  |  | 2026-02-21 | 2026-02-21 | Mohit Arora | JHU CSSE dataset collected | Done | bar: 2021-11-01 to 2021-11-06
| 2.1 Source and schema verification |  | 2026-02-21 | 2026-02-21 | Mohit Arora | Validated source metadata | Done
3. Data Preparation |  |  | 2026-02-21 | 2026-02-21 | Mohit Arora | Cleaned and transformed data | Done
| 3.1 Missing value handling and validation |  | 2026-02-21 | 2026-02-21 | Mohit Arora | Validated clean dataset | Done
| 3.2 Wide-to-long transformation |  | 2026-02-21 | 2026-02-21 | Mohit Arora | Long-format time-series | Done
| 3.3 DailyNewCases derivation |  | 2026-02-21 | 2026-02-21 | Mohit Arora | Feature-ready dataset | Done
4. Exploratory Data Analysis |  |  | 2026-02-21 | 2026-02-22 | Nishita | Trend and pattern analysis | Done
| 4.1 Country-level trend analysis |  | 2026-02-21 | 2026-02-22 | Nishita | Country comparison findings | Done
| 4.2 Wave and monthly trend analysis |  | 2026-02-22 | 2026-02-22 | Nishita | Wave summary report | Done
5. Feature Engineering |  |  | 2026-02-22 | 2026-02-22 | Sourabh Panchal | Model feature vectors | Done
| 5.1 Temporal feature creation |  | 2026-02-22 | 2026-02-22 | Sourabh Panchal | Day/Week/Month features | Done
| 5.2 Train-test split (80/20) |  | 2026-02-22 | 2026-02-22 | Sourabh Panchal | Training/testing datasets | Done
6. Model Development |  |  | 2026-02-22 | 2026-02-22 | Sourabh Panchal | Trained regression models | Done
| 6.1 Linear Regression model training |  | 2026-02-22 | 2026-02-22 | Sourabh Panchal | LR model + metrics | Done
| 6.2 Random Forest benchmark |  | 2026-02-22 | 2026-02-22 | Sourabh Panchal | RF benchmark metrics | Done
| 6.3 Best model selection |  | 2026-02-22 | 2026-02-22 | Sourabh Panchal | Final model selected | Done
7. Validation and Testing |  |  | 2026-02-23 | 2026-02-23 | Nishita | Validation report | Done
| 7.1 Statistical significance testing |  | 2026-02-23 | 2026-02-23 | Nishita | Statistical test output | Done
| 7.2 Prediction verification |  | 2026-02-23 | 2026-02-23 | Sourabh Panchal | Verified predictions | Done
8. Documentation |  |  | 2026-02-22 | 2026-02-24 | Ayush Nagpal | Submission documents complete | Done
| 8.1 Action Plan completion |  | 2026-02-22 | 2026-02-23 | Ayush Nagpal | Final Action Plan | Done
| 8.2 Final Report completion |  | 2026-02-23 | 2026-02-24 | Ayush Nagpal | Final Report | Done
| 8.3 WBS worksheet completion |  | 2026-02-23 | 2026-02-24 | Ayush Nagpal | Completed WBS | Done
| 8.4 Presentation preparation |  | 2026-02-24 | 2026-02-24 | Ayush Nagpal | Final PPT | Done
9. Final QA and Submission |  |  | 2026-02-24 | 2026-02-24 | Prince Bhatia | Submission package | Done
| 9.1 Repository cleanup and structuring |  | 2026-02-24 | 2026-02-24 | Prince Bhatia | Organized repository | Done
| 9.2 ZIP packaging and final checklist |  | 2026-02-24 | 2026-02-24 | Prince Bhatia | Final ZIP package | Done
| 9.3 Submission readiness confirmation |  | 2026-02-24 | 2026-02-24 | Prince Bhatia | Ready for submission | Done